## Risk Register
Risk ID | Asset / Process | Risk Scenario | Threat | Vulnerability / Control Gap | Likelihood (1-5) | Impact (1-5) | Inherent Risk Score | Inherent Risk Level | Existing Controls / Assumptions | Risk Treatment | Recommended Actions | Risk Owner | Target Date | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Risk Score | Residual Risk Level | Status
R-01 | Employee accounts / Microsoft 365 | An attacker gains access to an employee account and accesses client documents. | Credential theft / phishing | Scenario assumption: MFA coverage has not been verified and may be inconsistent. | 4 | 5 |  |  | Simulated scenario; no real system evidence collected. | Mitigate | Verify MFA coverage; enforce MFA for all users; review privileged accounts; monitor sign-in alerts. | IT Manager | Within 30 days | 2 | 4 |  |  | Proposed
R-02 | Client document storage | Unauthorised disclosure of client files due to excessive access permissions. | Insider misuse / compromised account | Scenario assumption: access permissions have not been reviewed recently. | 3 | 5 |  |  | Simulated scenario; permissions have not been independently checked. | Mitigate | Review access groups; apply least privilege; remove unnecessary access; schedule quarterly reviews. | Data Owner | Within 45 days | 2 | 4 |  |  | Proposed
R-03 | Backup and recovery | Critical business data cannot be restored after accidental deletion or ransomware. | Ransomware / operational error | Scenario assumption: restore testing frequency is unknown. | 3 | 5 |  |  | Backup arrangements are assumed to exist but have not been verified. | Mitigate | Confirm backup scope; protect backup credentials; test restoration; document recovery objectives. | IT Operations | Within 60 days | 2 | 4 |  |  | Proposed
R-04 | Security monitoring | Suspicious sign-ins or endpoint activity are not detected promptly. | Account compromise / malware | Scenario assumption: log coverage and alert-review procedures are undocumented. | 3 | 4 |  |  | No real log sources or monitoring evidence reviewed. | Mitigate | Define critical log sources; enable relevant alerts; assign alert-review ownership; test escalation. | Security Lead | Within 60 days | 2 | 3 |  |  | Proposed
R-05 | Incident response | A security incident is handled inconsistently, delaying containment and recovery. | Phishing / malware / data exposure | Scenario assumption: incident response plan and exercise records have not been reviewed. | 3 | 4 |  |  | The scenario does not establish whether a formal plan exists. | Mitigate | Document reporting and escalation steps; assign incident roles; conduct a tabletop exercise; record lessons learned. | IT Manager | Within 60 days | 2 | 3 |  |  | Proposed
R-06 | Employee security awareness | An employee follows a malicious link and discloses credentials. | Phishing / social engineering | Scenario assumption: awareness training completion and effectiveness are unknown. | 4 | 4 |  |  | No real training records or phishing simulation results reviewed. | Mitigate | Deliver role-appropriate awareness training; provide a reporting channel; measure completion and follow-up. | HR + IT | Within 90 days | 2 | 3 |  |  | Proposed
R-07 | Third-party IT services | A supplier incident affects the confidentiality or availability of company data. | Supplier compromise / service outage | Scenario assumption: supplier security reviews and contractual requirements are not confirmed. | 3 | 4 |  |  | No supplier contracts or assurance reports reviewed. | Mitigate | Identify critical suppliers; assess security requirements; review assurance evidence; define incident notification obligations. | Procurement + IT | Within 90 days | 2 | 3 |  |  | Proposed

## Scoring Guide
Risk Register Scoring Guide | Definition
Likelihood 1 | Rare
Likelihood 2 | Unlikely
Likelihood 3 | Possible
Likelihood 4 | Likely
Likelihood 5 | Almost certain
Impact 1 | Insignificant
Impact 2 | Minor
Impact 3 | Moderate
Impact 4 | Major
Impact 5 | Severe
Risk score | Likelihood × Impact (range 1–25)
Low | 1–7
Medium | 8–14
High | 15–25
Important limitation | These thresholds are illustrative project assumptions, not prescribed ISO 27001 thresholds. Confirm the organisation's risk criteria before real use.
Evidence status | All company conditions are simulated assumptions; no real organisation was audited. Validate evidence before treating a control as implemented or missing.