## CSF Gap Assessment
CSF Function | Category / Outcome Area | Current State (Simulated) | Target State | Gap / Improvement Need | Priority | Recommended Action | Suggested Owner | Proposed Timeline | Evidence to Validate | Status
Govern | Organisational context and risk strategy | Assumption: cybersecurity responsibilities and risk appetite have not been documented for this exercise. | Management-approved cybersecurity responsibilities, risk appetite, and decision-making process. | Governance arrangements and risk acceptance criteria require confirmation. | High | Define risk ownership, approval authority, escalation routes, and risk acceptance criteria. | Management + IT Manager | Within 45 days | Approved policy, role assignments, risk appetite statement, meeting records. | Proposed
Identify | Asset management | Assumption: a complete inventory of systems, devices, data, and critical services has not been provided. | Maintained inventory of key assets, owners, dependencies, and business criticality. | Asset coverage and ownership are unverified. | High | Create and maintain an asset inventory; assign owners; identify critical information and services. | IT Operations | Within 45 days | Asset register, ownership records, review history. | Proposed
Protect | Identity and access management | Assumption: MFA coverage and periodic access reviews have not been verified. | Access is authorised, least-privilege based, and protected with appropriate authentication. | MFA enforcement, privileged access, and access-review practices require evidence. | High | Review accounts and permissions; enforce MFA where appropriate; remove unnecessary access; document exceptions. | IT Manager | Within 30 days | MFA policy/configuration, access review records, privileged account inventory. | Proposed
Protect | Data security | Assumption: data classification and handling requirements have not been provided. | Sensitive information is classified and handled according to business and legal requirements. | Classification, retention, sharing, and disposal arrangements are unverified. | High | Define data categories and handling rules; review external sharing; set retention and secure disposal practices. | Data Owners + IT | Within 60 days | Data classification policy, sharing configuration, retention rules. | Proposed
Detect | Continuous monitoring | Assumption: log coverage, alert ownership, and review cadence have not been confirmed. | Relevant events are logged and monitored with defined responsibilities and escalation. | Detection coverage and alert handling are unverified. | High | Identify critical log sources; configure appropriate alerts; assign review ownership and escalation procedures. | Security Lead | Within 60 days | Log source inventory, sample alerts, review records, escalation runbook. | Proposed
Respond | Incident management | Assumption: the incident response plan and exercise results have not been reviewed. | Incidents can be reported, assessed, contained, communicated, and documented consistently. | Roles, communications, and response procedures need validation. | Medium | Document incident workflow and responsibilities; conduct a tabletop exercise; track improvement actions. | IT Manager | Within 60 days | Incident plan, contact list, exercise results, lessons-learned tracker. | Proposed
Recover | Recovery planning and testing | Assumption: recovery objectives and restoration-test evidence have not been provided. | Critical services have defined recovery objectives and tested recovery procedures. | Recoverability and restoration time are unverified. | High | Identify critical services; agree recovery objectives; test backup restoration and document results. | IT Operations + Business Owners | Within 60 days | Recovery plan, approved objectives, backup and restoration test records. | Proposed
Govern | Third-party risk oversight | Assumption: supplier criticality and security review records have not been provided. | Critical suppliers are identified and assessed according to risk and service importance. | Supplier oversight and security obligations require validation. | Medium | Create a critical supplier list; assess security risks; review contractual security and incident notification requirements. | Procurement + IT | Within 90 days | Supplier inventory, risk reviews, contract clauses, assurance evidence. | Proposed

## Scoring & Notes
Item | Guidance
Framework | NIST Cybersecurity Framework (CSF) 2.0. The six functions are Govern, Identify, Protect, Detect, Respond, and Recover.
Assessment basis | Current-state descriptions are simulated assumptions for a fictional organisation, not verified findings from a real company.
Priority | Priorities are proposed for this learning scenario and should be validated against business context and approved risk criteria.
Target state | Target states describe desired outcomes, not a claim that the organisation has achieved them.
Evidence | Collect or create appropriate evidence in a real assessment before confirming whether an outcome is met.
Disclaimer | This is an educational gap assessment, not a formal audit, certification, or official NIST assessment.